## Sheet1
Iteration | Assignment | Task | Check Point
Iteration 1 | Check UWP User Data API | Contacts API | 2016-02-01
|  | Text Message API | 2016-02-01
|  | Phone Call Record | 2016-02-01
| Chcek Azure Service Availability | Storage Design | 2016-02-15
|  | Login Design | 2016-02-15
| Develop Android Client | Set up Android Decelopment Envivronment | 2016-02-15
|  | UI Design | 2016-02-15
|  | Scan Contacts Data | 2016-02-16
|  | Scan Text Messages Data | 2016-02-16
|  | Scan Phone Calls Data | 2016-02-17
|  | Package User Data into Json | 2016-02-17
|  | Create Azure Blob Account | 2016-02-18
|  | Install Azure Lib on Android Platform | 2016-02-18
|  | Upload User Data Package | 2016-02-18
|  | Android UI Optimization | 2016-02-22
|  | Login | 2016-02-29
| Develop UWP Client | UI Design | 2016-03-07
|  | Login | 2016-03-07
|  | Download User Data Package | 2016-03-07
|  | Write Contacts Data | 2016-03-14
|  | Write Text Message Data | 2016-03-14
|  | Write Phone Call Record Data | 2016-03-14
|  | UWP UI Optimization | 2016-03-21